## Slide 1: LAC Mentorship Program Mentorship Overview
Disability Support Program
December 2025

## Slide 2
Table of Contents
LAC Mentorship Program
Objective, Purpose and Approach
Project Overview
Mentorship Overview
Outline the objectives and areas of support available for building an effective and sustainable LAC mentorship program.
Todays Objectives

## Slide 3
Objective, Purpose and Approach
Establish a sustainable mentorship program through connecting Subject Matter Experts (SMEs) with DSP Local Area Coordinator (LAC) Team Leads to build their knowledge, skills, and confidence to guide and support LACs effectively as DSP expands support planning under the IF model.
Objective
To ensure LACs have the practical guidance they need by equipping Team Leads to mentor and support them as they work alongside individuals, helping them plan for and live their idea of a good life.
Purpose
Approach
When developing the LAC Mentorship Program, we will take a similar approach to the development of the IPSC Mentorship Program, which has enabled IPSCs to connect with two dedicated Subject Matter Experts. LAC Team Leads will have the opportunity to connect with Ralph Broad, a key expert in Local Area Coordination, based out of Wales.
We are proposing the creation of an LAC Mentorship program with Subject Matter Expert, Ralph Broad, to empower LAC Team Leads to share knowledge with their broader Local Area Coordination team.

## Slide 4
Project Overview
Audience: LAC TLs (TLs to share learnings with LACs)
Proposed Availability: 2 days/month (≈ half-day/week) Office hours style + optional combined session for all TLs (TBD)
Scheduling: Calendly link setup (already set up for IPSC mentorship; can be extended for this program)
Primary DSP Contact: Kate Lowe, (Tricia Murray as needed for key decisions, final approvals)
Project Team : Ralph Broad (SME), Kate Lowe (DSP), Neha Upadhyay (DP), Jenna Levangie (DP)
Project Approach:
Proposed Timeline (December – Early February):
Weeks 1–4: Gather inputs from DSP & Ralph
Weeks 5-6: Finalize scope, set up admin items (e.g. Calendly setup, schedule launch meeting)
Completion Milestone: Tricia to hold a launch meeting for LAC TLs to kick off the program. Mentorship program delivery commences with Ralph.